## Sheet1
Deliverables |  | Estimate Hours of Work | Start Date (W/C) | End Date (end of W/C) | Milestones (W/C)
[5 empty] | 2020-10-01 |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | 2021-01-01 |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | 2021-04-01 |  |  |  | 2021-05-01
[5 empty] | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24
Sprint 0: Planning & Preparation | Create project initiation (inlcuding market research, project vision, objectives, & risk plan) | 5 | 2020-10-05 | 2020-10-11
| Create and populate backlog | 3 | 2020-10-05 | 2020-10-11
| Set up repository & web hosting, organise important documents (report, notes, minutes, etc.) | 1 | 2020-10-05 | 2020-10-11
| Research frameworks & tools to use | 4 | 2020-10-05 | 2020-10-11
| Create requirements and use cases for both users | 5 | 2020-10-05 | 2020-10-18
| Create project plan & Gantt chart | 10 | 2020-10-12 | 2020-10-18
| Design system flowchart | 5 | 2020-10-19 | 2020-10-26
| Create UI design | 3 | 2020-10-19 | 2020-10-26
| Design database schema | 4 | 2020-10-19 | 2020-10-26
Sprint 1: Facility focused | Set up app's initial pages (index, dashboard, login, etc.) & install Bootstrap to system | 3 | 2020-10-26 | 2020-11-01
| Create SQL statements for database | 3 | 2020-10-26 | 2020-11-01
| Allow facility to sign up | 4 | 2020-11-02 | 2020-11-08
| Allow facility to log in | 2 | 2020-11-02 | 2020-11-08
| List all active members | 6 | 2020-11-09 | 2020-11-15
| List all member requests | 1 | 2020-11-09 | 2020-11-15
| List all idle members (declined + inactive) | 2 | 2020-11-09 | 2020-11-15
Sprint 2: Member focused | Allow member to sign up | 3 | 2020-11-16 | 2020-11-22
| Allow member to log in | 2 | 2020-11-16 | 2020-11-22
| Allow facility to accept/decline member signup requests | 3 | 2020-11-16 | 2020-11-22
| Pending/inactive/declined members to have a "Verify member" page to eliminate unauthorised access | 4 | 2020-11-23 | 2020-12-06
| Display a member's access times to the member | 4 | 2020-11-23 | 2020-12-06
Sprint 3: Management focused | Allow facility to view all a member's details in a separate page ("manage member" page) | 5 | 2020-12-07 | 2020-12-13
| Allow facility to change a member's account status | 3 | 2020-12-14 | 2020-12-20
| Allow facility to view a member's access times | 1 | 2020-12-14 | 2020-12-20
| Allow facility to alter a member's access times | 3 | 2020-12-21 | 2020-12-27
Sprint 4: Livestream focused | Conduct further research into method of approach for implementing livestream | 10 | 2020-12-28 | 2021-01-03
| Allow facility to create a new livestream | 6 | 2021-01-04 | 2021-01-10
| Display all available livestreams to facility | 5 | 2021-01-04 | 2021-01-10
| Display all available livestreams to member | 3 | 2021-01-04 | 2021-01-10
| Allow member to ONLy access a livestream within their access times | 4 | 2021-01-11 | 2021-01-17
| Display popup message for members who are not within their "access times" | 1 | 2021-01-11 | 2021-01-17
| Allow facility to edit an existing livestream | 5 | 2021-01-18 | 2021-01-24
| Allow facility to delete an existing livestream | 2 | 2021-01-18 | 2021-01-24
Sprint 5: Message focused | Allow facility to issue a new message/notification to their members | 8 | 2021-01-25 | 2021-01-31
| Allow facility to view all existing messages | 5 | 2021-02-01 | 2021-02-07
| Allow member to view all existing messages | 2 | 2021-02-01 | 2021-02-07
Sprint 6: Testing | Create video demonstration for ETA | 16 | 2021-02-08 | 2021-02-14
| Inform ETA of development state + request feedback from video demo | 5 | 2021-02-08 | 2021-02-14
| Log feedback received from ETA for future developments + improvements | 2 | 2021-02-15 | 2021-02-21
| Create documentation for facilities on how to use SafeGaze | 6 | 2021-02-22 | 2021-02-28
Sprint 7: Finalisation | Adjust system to resolve potental errors/bugs found in testing | 10 | 2021-03-01 | 2021-03-07
| Refine UI styling | 6 | 2021-03-08 | 2021-03-14
| Create showcase materials | 14 | 2021-03-08 | 2021-04-04
| Project report finalisation | N/A | 2021-04-05 | 1900-01-15