## Sheet1
Deliverables |  | Estimate Hours of Work
Sprint 0: Planning & Preparation | Create project initiation (inlcuding market research, project vision, objectives, & risk plan) | 5
| Create and populate backlog | 3
| Set up repository & web hosting, organise important documents (report, notes, minutes, etc.) | 1
| Research frameworks & tools to use | 4
| Create requirements and use cases for both users | 5
| Create project plan & Gantt chart | 10
| Design system flowchart | 5
| Create UI design | 3
| Design database schema | 4
Sprint 1: Facility focused | Set up app's initial pages (index, dashboard, login, etc.) & install Bootstrap to system | 3
| Create SQL statements for database | 3
| Allow facility to sign up | 4
| Allow facility to log in | 2
| List all active members | 6
| List all member requests | 1
| List all idle members (declined + inactive) | 2
Sprint 2: Member focused | Allow member to sign up | 3
| Allow member to log in | 2
| Allow facility to accept/decline member signup requests | 3
| Pending/inactive/declined members to have a "Verify member" page to eliminate unauthorised access | 4
| Display a member's access times to the member | 4
Sprint 3: Management focused | Allow facility to view all a member's details in a separate page ("manage member" page) | 5
| Allow facility to change a member's account status | 3
| Allow facility to view a member's access times | 1
| Allow facility to alter a member's access times | 3
Sprint 4: Livestream focused | Conduct further research into method of approach for implementing livestream | 10
| Allow facility to create a new livestream | 6
| Display all available livestreams to facility | 5
| Display all available livestreams to member | 3
| Allow member to ONLY access a livestream within their access times | 4
| Display popup message for members who are not within their "access times" | 1
| Allow facility to edit an existing livestream | 5
| Allow facility to delete an existing livestream | 2
Sprint 5: Message focused | Allow facility to issue a new message/notification to their members | 8
| Allow facility to view all existing messages | 5
| Allow member to view all existing messages | 2
Sprint 6: Testing | Create video demonstration for ETA | 16
| Inform ETA of development state + request feedback from video demo | 5
| Log feedback received from ETA for future developments + improvements | 2
| Create documentation for facilities on how to use SafeGaze | 6
Sprint 7: Finalisation | Adjust system to resolve potental errors/bugs found in testing | 10
| Refine UI styling | 6
| Create showcase materials | 14
| Project report finalisation | N/A